## Scope with Sub Task
Sl No | Category | Dwg Code | Description (Task) | Sub Task | QTY | UNIT | Breakdown % | RATE | AMOUNT
1 |  |  | PARTITION AND LINING
1.01 | Partition / Lining |  | 100mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 4.0m. Location :Veterinary Clinic |  | 472 | Sqm |  | 108 | 50976
|  |  |  | Frame 01 | 472 | Sqm | 30% | 32.4 | 15292.8
|  |  |  | Gypsum Board 01 | 472 | Sqm | 15% | 16.2 | 7646.4
|  |  |  | Rockwool | 472 | Sqm | 10% | 10.8 | 5097.6
|  |  |  | Gypsum Board 02 | 472 | Sqm | 15% | 16.2 | 7646.4
|  |  |  | Taping Jointing 01 | 472 | Sqm | 15% | 16.2 | 7646.4
|  |  |  | Taping Jointing 02 | 472 | Sqm | 10% | 10.8 | 5097.6
|  |  |  | Sanding | 472 | Sqm | 5% | 5.4 | 2548.8
1.02 | Partition / Lining |  | 200 mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 4.0m. Location :Veterinary Clinic |  | 72 | Sqm |  | 210 | 15120
|  |  |  | Frame 01 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Frame 02 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Gypsum Board 01 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Rockwool | 72 | Sqm | 10% | 21 | 1512
|  |  |  | Gypsum Board 02 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Taping Jointing 01 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Taping Jointing 02 | 72 | Sqm | 10% | 21 | 1512
|  |  |  | Sanding | 72 | Sqm | 5% | 10.5 | 756
1.03 | Partition / Lining |  | 100mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 1.2m. Location :Veterinary Clinic |  | 13.2 | Sqm |  | 110 | 1452
|  |  |  | Frame 01 | 13.2 | Sqm | 30% | 33 | 435.6
|  |  |  | Gypsum Board 01 | 13.2 | Sqm | 15% | 16.5 | 217.8
|  |  |  | Rockwool | 13.2 | Sqm | 10% | 11 | 145.2
|  |  |  | Gypsum Board 02 | 13.2 | Sqm | 15% | 16.5 | 217.8
|  |  |  | Taping Jointing 01 | 13.2 | Sqm | 15% | 16.5 | 217.8
|  |  |  | Taping Jointing 02 | 13.2 | Sqm | 10% | 11 | 145.2
|  |  |  | Sanding | 13.2 | Sqm | 5% | 5.5 | 72.6
1.04 | Partition / Lining |  | Supply and installation of gypsum lining on the existing block wall 12.5mm thick Gypsum board with 75mm stud of height max upto 4.0m. Location :Veterinary Clinic |  | 188 | Sqm |  | 95 | 17860
|  |  |  | Frame 01 | 188 | Sqm | 30% | 28.5 | 5358
|  |  |  | Gypsum Board 01 | 188 | Sqm | 15% | 14.25 | 2679
|  |  |  | Taping Jointing 01 | 188 | Sqm | 15% | 14.25 | 2679
|  |  |  | Taping Jointing 02 | 188 | Sqm | 10% | 9.5 | 1786
|  |  |  | Sanding | 188 | Sqm | 5% | 4.75 | 893
2 |  |  | FLOORING WORKS
2.01 | Floor |  | F-102 VINYL FLOORING Supply of flooring - Straight Pattern as per the sample submitted and approved by the client, to be installed by Glue on smooth, levelled, clear and dry floor. Considered oak wood effect sheet vinyl as per client instruction Suitable for clinics. |  | 166 | Sqm |  | 140 | 23240
2.02 | Floor |  | F-102 VINYL FLOORING Installation of the flooring including self leveling |  | 166 | Sqm |  | 80 | 13280
|  |  |  | Self Levelling | 166 | Sqm | 60% | 48 | 7968
|  |  |  | Installation of Vinyl | 166 | Sqm | 40% | 32 | 5312
2.03 | Floor |  | F-300 MOSAIC TILE FLOORING Supply and installation of tile flooring 60x120x9mm Porcelain Matt P.C Rate of AED 110.00 per sqm |  | 52 | Sqm |  | 165 | 8580
|  |  |  | Tile Fixing | 52 | Sqm | 90% | 148.5 | 7722
|  |  |  | Grout | 52 | Sqm | 10% | 16.5 | 858
2.04 | Floor |  | F-305 TILE FLOORING Supply and installation of tile flooring 20x120x9mm Porcelain Matt. P.C Rate of AED 90.00 per sqm Reception |  | 18 | Sqm |  | 145 | 2610
|  |  |  | Tile Fixing | 18 | Sqm | 90% | 130.5 | 2349
|  |  |  | Grout | 18 | Sqm | 10% | 14.5 | 261
2.05 | Floor |  | SKIRTING Supply and installation of wooden skirting |  | 299 | Lm |  | 60 | 17940
|  |  |  | Skirting Fixing | 299 | Sqm | 90% | 54 | 16146
|  |  |  | Grout | 299 | Sqm | 10% | 6 | 1794
2.06 | Floor |  | Trim Supply and installation of transition strips on areas with different finishes |  | 12 | Lm |  | 90 | 1080
3 |  |  | WALL FINISHES
3.01 | Paint |  | PAINT FINISH-W200 Supply and apply of paint finish Location : GF/MF Considered alternative option Jotun Fenomastic paint finish |  | 105 | Sqm |  | 30 | 3150
|  |  |  | Primer | 105 | Sqm | 15% | 4.5 | 472.5
|  |  |  | Stucco 01 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Stucco 02 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Paint 01 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Paint 02 | 105 | Sqm | 25% | 7.5 | 787.5
3.02 | Paint |  | PAINT FINISH-W202 Supply and apply of new paint finish Location : GF/MF Jotun Fenomastic or equivalent |  | 39 | Sqm |  | 30 | 1170
|  |  |  | Primer | 39 | Sqm | 15% | 4.5 | 175.5
|  |  |  | Stucco 01 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Stucco 02 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Paint 01 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Paint 02 | 39 | Sqm | 25% | 7.5 | 292.5
3.03 | Paint |  | ANTIMICROBIAL PAINT FINISH -W204 Supply and installation of new paint finish Location : GF/MF Jotun or equivalent |  | 750 | Sqm |  | 40 | 30000
|  |  |  | Primer | 750 | Sqm | 15% | 6 | 4500
|  |  |  | Stucco 01 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Stucco 02 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Paint 01 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Paint 02 | 750 | Sqm | 25% | 10 | 7500
4 |  |  | CEILING WORKS
4.01 | Ceiling |  | GYPSUM CEILING Supply and installation of 12.5mm thick one layer of MR gypsum board ceiling including paint finish ( Jotun Fenomastic or Equivalent) Location : Vet Reception Area |  | 70 | Sqm |  | 140 | 9800
|  |  |  | Frame 01 | 70 | Sqm | 40% | 56 | 3920
|  |  |  | Gypsum Board 01 | 70 | Sqm | 25% | 35 | 2450
|  |  |  | Taping Jointing 01 | 70 | Sqm | 15% | 21 | 1470
|  |  |  | Taping Jointing 02 | 70 | Sqm | 15% | 21 | 1470
|  |  |  | Sanding | 70 | Sqm | 5% | 7 | 490
4.02 | Ceiling |  | GYPSUM CEILING - 60 x 60 Supply and installation of 60 x 60 ceiling tile |  | 249 | Sqm |  | 110 | 27390
|  |  |  | Frame 01 | 249 | Sqm | 40% | 44 | 10956
|  |  |  | Tile Fixing | 249 | Sqm | 25% | 27.5 | 6847.5
4.03 | Ceiling |  | GYPSUM CEILING COVE Supply and installation of gypsum cove for the LED and cut outs for the lights and AC grills including paint finish ( Jotun Fenomastic or Equivalent) Location : Vet Reception Area |  | 1 | Item |  | 5000 | 5000
|  |  |  | Frame 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Gypsum Board 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Taping Jointing 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Taping Jointing 02 | 1 | Nos | 5% | 250 | 250
|  |  |  | Sanding | 1 | Nos | 5% | 250 | 250
|  |  |  | Paint | 1 | Nos | 25% | 1250 | 1250
|  |  |  | Cut Outs | 1 | Nos | 35% | 1750 | 1750
4.04 | Joinery |  | WOODEN CEILING AT THE VET AREA supply and installation of wooden ceiling at the VET area - MDF with veneer finish Area considered : 20 Sqm Chandelier is excluded |  | 1 | Item |  | 13387 | 13387
|  |  |  | Frame 01 | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Veneer | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Polish | 1 | Nos | 15% | 2008.05 | 2008.05
|  |  |  | Assembly | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Site Fixing | 1 | Nos | 25% | 3346.75 | 3346.75
5 |  |  | GLASS AND ALUMINUM
5.01 | Glass |  | Supply and installation of fixed glass partition. max.ht up to 3m |  | 24 | Sqm |  | 450 | 10800
|  |  |  | Channels | 24 | Nos | 20% | 90 | 2160
|  |  |  | Glass Fixing | 24 | Nos | 60% | 270 | 6480
|  |  |  | Finishing Joints | 24 | Nos | 15% | 67.5 | 1620
|  |  |  | Cleaning | 24 | Nos | 5% | 22.5 | 540
6 |  |  | JOINERY
| Joinery |  | Manufacture, supply and installation of Reception Counter with build in storage made of MDF with all related works as per design. Exclude Signage |  | 1 | Nos |  | 20350 | 20350
|  |  |  | Frame 01 | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Veneer | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Polish | 1 | Nos | 10% | 2035 | 2035
|  |  |  | Assembly | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Site Fixing | 1 | Nos | 30% | 6105 | 6105
7 | Joinery |  | Manufacture, supply and installation of L Shape Planter Box made of MDF with all related works as per design. Exclude Plants |  | 1 | Nos |  | 4530 | 4530
|  |  |  | Frame 01 | 1 | Nos | 30% | 1359 | 1359
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1359 | 1359
|  |  |  | Site Fixing | 1 | Nos | 40% | 1812 | 1812
8 | Joinery |  | Manufacture, supply and installation of Banquette Seating with Projections made of MDF with all related works as per design. Exclude: Plants ¦ @ Cat Waiting Area Note-Aed 60-70 Leather consider |  | 1 | Nos |  | 5850 | 5850
|  |  |  | Frame 01 | 1 | Nos | 30% | 1755 | 1755
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1755 | 1755
|  |  |  | Site Fixing | 1 | Nos | 40% | 2340 | 2340
9 | Joinery |  | Manufacture, supply and installation of Two Tier Banquette Seating with Steps at center made of MDF with all related works as per design. @ Dog Waiting Area Note-Aed 60-70 Leather consider |  | 1 | Nos |  | 5000 | 5000
|  |  |  | Frame 01 | 1 | Nos | 30% | 1500 | 1500
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1500 | 1500
|  |  |  | Site Fixing | 1 | Nos | 40% | 2000 | 2000
10 | Joinery |  | Manufacture, supply and installation of Banquette Seating made of MDF with all related works as per design. @ Dog Waiting Area |  | 1 | Nos |  | 3350 | 3350
|  |  |  | Frame 01 | 1 | Nos | 30% | 1005 | 1005
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1005 | 1005
|  |  |  | Site Fixing | 1 | Nos | 40% | 1340 | 1340
11 | Joinery |  | Manufacture, supply and installation of Planter Box made of MDF with all related works as per design. Exclude: Plants @ Behing Banquette Sitting at Cat Waiting Area |  | 1 | Nos |  | 6905 | 6905
|  |  |  | Frame 01 | 1 | Nos | 30% | 2071.5 | 2071.5
|  |  |  | Laminate Finish | 1 | Nos | 30% | 2071.5 | 2071.5
|  |  |  | Site Fixing | 1 | Nos | 40% | 2762 | 2762
12 | Joinery |  | Manufacture, supply and installation of DB Wall Cladding Cabinet Type made of MDF all related works as per design. |  | 1 | Nos |  | 7150 | 7150
|  |  |  | Frame 01 | 1 | Nos | 30% | 2145 | 2145
|  |  |  | Laminate Finish | 1 | Nos | 30% | 2145 | 2145
|  |  |  | Site Fixing | 1 | Nos | 40% | 2860 | 2860
13 | Joinery |  | Manufacture, supply and installation of Display Cabinet with Under Storage made of MDF with all related works as per design. @ Near Reception Desk Note-LED Light Excluded |  | 2 | Nos |  | 5000 | 10000
|  |  |  | Frame 01 | 2 | Nos | 30% | 1500 | 3000
|  |  |  | Laminate Finish | 2 | Nos | 30% | 1500 | 3000
|  |  |  | Site Fixing | 2 | Nos | 40% | 2000 | 4000
14 | Joinery |  | Manufacture, supply and installation of Cabinet with Sink made of MDF with all related works as per design. Exclude all Appliences and MEP works |  | 1 | Nos |  | 19880 | 19880
|  |  |  | Frame 01 | 1 | Nos | 30% | 5964 | 5964
|  |  |  | Laminate Finish | 1 | Nos | 20% | 3976 | 3976
|  |  |  | Site Fixing | 1 | Nos | 50% | 9940 | 9940
15 | Joinery |  | Manufacture, supply and installation of Cabinet with Sink made of MDF with all related works as per design. Exclude all Appliences and MEP works |  | 1 | Nos |  | 22500 | 22500
|  |  |  | Frame 01 | 1 | Nos | 30% | 6750 | 6750
|  |  |  | Laminate Finish | 1 | Nos | 20% | 4500 | 4500
|  |  |  | Site Fixing | 1 | Nos | 50% | 11250 | 11250
16 | Joinery |  | Manufacture, supply and installationn of Preparation Cabinet made of MDF with all related works as per design. |  | 1 | Nos |  | 5600 | 5600
|  |  |  | Frame 01 | 1 | Nos | 30% | 1680 | 1680
|  |  |  | Laminate Finish | 1 | Nos | 20% | 1120 | 1120
|  |  |  | Site Fixing | 1 | Nos | 50% | 2800 | 2800
17 | Joinery |  | Manufacture, supply and installationn of Preparation Table made of MDF with all related works as per design. |  | 2 | Nos |  | 6500 | 13000
|  |  |  | Frame 01 | 2 | Nos | 30% | 1950 | 3900
|  |  |  | Laminate Finish | 2 | Nos | 20% | 1300 | 2600
|  |  |  | Site Fixing | 2 | Nos | 50% | 3250 | 6500
18 | Joinery |  | Manufacture, supply and installation of Wooden Battern Ceiling made of MDF with all related works as per design. Note-200 mm hight consider |  | 1 | Nos |  | 15000 | 15000
|  |  |  | Frame 01 | 1 | Nos | 30% | 4500 | 4500
|  |  |  | Laminate Finish | 1 | Nos | 20% | 3000 | 3000
|  |  |  | Site Fixing | 1 | Nos | 50% | 7500 | 7500
19 | Joinery |  | Timber doors and frames; including ironmongery, architrave, fittings, fixings and accessories; all in accordance with the drawings and Specifications. Single leaf concealed door closer |  | 8 | Nos |  | 3100 | 24800
|  |  |  | Frame 01 | 8 | Nos | 30% | 930 | 7440
|  |  |  | Laminate Finish | 8 | Nos | 20% | 620 | 4960
|  |  |  | Site Fixing | 8 | Nos | 50% | 1550 | 12400
20 | Joinery |  | Timber doors and frames; including ironmongery, architrave, fittings, fixings and accessories; all in accordance with the drawings and Specifications. Single leaf , with vision panel concealed door closer |  | 1 | Nos |  | 3500 | 3500
|  |  |  | Frame 01 | 1 | Nos | 30% | 1050 | 1050
|  |  |  | Laminate Finish | 1 | Nos | 20% | 700 | 700
|  |  |  | Site Fixing | 1 | Nos | 50% | 1750 | 1750

## Daily Progress w Pic Report
Sl No | Category | Dwg Code | Description (Task) | Sub Task | QTY | UNIT | Breakdown % | RATE | AMOUNT | Cum Qty till yesterday | Today's Qty | Balance Qty | Cum Amt till yesterday | Today's Amt | Balance Amt
1 |  |  | PARTITION AND LINING
1.01 | Partition / Lining |  | 100mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 4.0m. Location :Veterinary Clinic |  | 472 | Sqm |  | 108 | 50976 | 217.5 | 61.6 | 192.9 | 23490 | 6652.8 | 20833.2
|  |  |  | Frame 01 | 472 | Sqm | 30% | 32.4 | 15292.8 | 400 | 72 | 0 | 12960 | 2332.8 | 0
|  |  |  | Gypsum Board 01 | 472 | Sqm | 15% | 16.2 | 7646.4 | 300 | 100 | 72 | 4860 | 1620 | 1166.4
|  |  |  | Rockwool | 472 | Sqm | 10% | 10.8 | 5097.6 | 300 | 100 | 72 | 3240 | 1080 | 777.6
|  |  |  | Gypsum Board 02 | 472 | Sqm | 15% | 16.2 | 7646.4 | 150 | 100 | 222 | 2430 | 1620 | 3596.4
|  |  |  | Taping Jointing 01 | 472 | Sqm | 15% | 16.2 | 7646.4 | 0 |  | 472 | 0 | 0 | 7646.4
|  |  |  | Taping Jointing 02 | 472 | Sqm | 10% | 10.8 | 5097.6 | 0 |  | 472 | 0 | 0 | 5097.6
|  |  |  | Sanding | 472 | Sqm | 5% | 5.4 | 2548.8 | 0 |  | 472 | 0 | 0 | 2548.8
1.02 | Partition / Lining |  | 200 mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 4.0m. Location :Veterinary Clinic |  | 72 | Sqm |  | 210 | 15120
|  |  |  | Frame 01 | 72 | Sqm | 15% | 31.5 | 2268 |  |  | 72
|  |  |  | Frame 02 | 72 | Sqm | 15% | 31.5 | 2268 |  |  | 72
|  |  |  | Gypsum Board 01 | 72 | Sqm | 15% | 31.5 | 2268 |  |  | 72
|  |  |  | Rockwool | 72 | Sqm | 10% | 21 | 1512 |  |  | 72
|  |  |  | Gypsum Board 02 | 72 | Sqm | 15% | 31.5 | 2268 |  |  | 72
|  |  |  | Taping Jointing 01 | 72 | Sqm | 15% | 31.5 | 2268 |  |  | 72
|  |  |  | Taping Jointing 02 | 72 | Sqm | 10% | 21 | 1512 |  |  | 72
|  |  |  | Sanding | 72 | Sqm | 5% | 10.5 | 756 |  |  | 72
1.03 | Partition / Lining |  | 100mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 1.2m. Location :Veterinary Clinic |  | 13.2 | Sqm |  | 110 | 1452
|  |  |  | Frame 01 | 13.2 | Sqm | 30% | 33 | 435.6 |  |  | 13.2
|  |  |  | Gypsum Board 01 | 13.2 | Sqm | 15% | 16.5 | 217.8 |  |  | 13.2
|  |  |  | Rockwool | 13.2 | Sqm | 10% | 11 | 145.2 |  |  | 13.2
|  |  |  | Gypsum Board 02 | 13.2 | Sqm | 15% | 16.5 | 217.8 |  |  | 13.2
|  |  |  | Taping Jointing 01 | 13.2 | Sqm | 15% | 16.5 | 217.8 |  |  | 13.2
|  |  |  | Taping Jointing 02 | 13.2 | Sqm | 10% | 11 | 145.2 |  |  | 13.2
|  |  |  | Sanding | 13.2 | Sqm | 5% | 5.5 | 72.6 |  |  | 13.2
1.04 | Partition / Lining |  | Supply and installation of gypsum lining on the existing block wall 12.5mm thick Gypsum board with 75mm stud of height max upto 4.0m. Location :Veterinary Clinic |  | 188 | Sqm |  | 95 | 17860
|  |  |  | Frame 01 | 188 | Sqm | 30% | 28.5 | 5358
|  |  |  | Gypsum Board 01 | 188 | Sqm | 15% | 14.25 | 2679
|  |  |  | Taping Jointing 01 | 188 | Sqm | 15% | 14.25 | 2679
|  |  |  | Taping Jointing 02 | 188 | Sqm | 10% | 9.5 | 1786
|  |  |  | Sanding | 188 | Sqm | 5% | 4.75 | 893
2 |  |  | FLOORING WORKS
2.01 | Floor |  | F-102 VINYL FLOORING Supply of flooring - Straight Pattern as per the sample submitted and approved by the client, to be installed by Glue on smooth, levelled, clear and dry floor. Considered oak wood effect sheet vinyl as per client instruction Suitable for clinics. |  | 166 | Sqm |  | 140 | 23240
2.02 | Floor |  | F-102 VINYL FLOORING Installation of the flooring including self leveling |  | 166 | Sqm |  | 80 | 13280
|  |  |  | Self Levelling | 166 | Sqm | 60% | 48 | 7968
|  |  |  | Installation of Vinyl | 166 | Sqm | 40% | 32 | 5312
2.03 | Floor |  | F-300 MOSAIC TILE FLOORING Supply and installation of tile flooring 60x120x9mm Porcelain Matt P.C Rate of AED 110.00 per sqm |  | 52 | Sqm |  | 165 | 8580
|  |  |  | Tile Fixing | 52 | Sqm | 90% | 148.5 | 7722
|  |  |  | Grout | 52 | Sqm | 10% | 16.5 | 858
2.04 | Floor |  | F-305 TILE FLOORING Supply and installation of tile flooring 20x120x9mm Porcelain Matt. P.C Rate of AED 90.00 per sqm Reception |  | 18 | Sqm |  | 145 | 2610
|  |  |  | Tile Fixing | 18 | Sqm | 90% | 130.5 | 2349
|  |  |  | Grout | 18 | Sqm | 10% | 14.5 | 261
2.05 | Floor |  | SKIRTING Supply and installation of wooden skirting |  | 299 | Lm |  | 60 | 17940
|  |  |  | Skirting Fixing | 299 | Sqm | 90% | 54 | 16146
|  |  |  | Grout | 299 | Sqm | 10% | 6 | 1794
2.06 | Floor |  | Trim Supply and installation of transition strips on areas with different finishes |  | 12 | Lm |  | 90 | 1080
3 |  |  | WALL FINISHES
3.01 | Paint |  | PAINT FINISH-W200 Supply and apply of paint finish Location : GF/MF Considered alternative option Jotun Fenomastic paint finish |  | 105 | Sqm |  | 30 | 3150
|  |  |  | Primer | 105 | Sqm | 15% | 4.5 | 472.5
|  |  |  | Stucco 01 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Stucco 02 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Paint 01 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Paint 02 | 105 | Sqm | 25% | 7.5 | 787.5
3.02 | Paint |  | PAINT FINISH-W202 Supply and apply of new paint finish Location : GF/MF Jotun Fenomastic or equivalent |  | 39 | Sqm |  | 30 | 1170
|  |  |  | Primer | 39 | Sqm | 15% | 4.5 | 175.5
|  |  |  | Stucco 01 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Stucco 02 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Paint 01 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Paint 02 | 39 | Sqm | 25% | 7.5 | 292.5
3.03 | Paint |  | ANTIMICROBIAL PAINT FINISH -W204 Supply and installation of new paint finish Location : GF/MF Jotun or equivalent |  | 750 | Sqm |  | 40 | 30000
|  |  |  | Primer | 750 | Sqm | 15% | 6 | 4500
|  |  |  | Stucco 01 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Stucco 02 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Paint 01 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Paint 02 | 750 | Sqm | 25% | 10 | 7500
4 |  |  | CEILING WORKS
4.01 | Ceiling |  | GYPSUM CEILING Supply and installation of 12.5mm thick one layer of MR gypsum board ceiling including paint finish ( Jotun Fenomastic or Equivalent) Location : Vet Reception Area |  | 70 | Sqm |  | 140 | 9800
|  |  |  | Frame 01 | 70 | Sqm | 40% | 56 | 3920
|  |  |  | Gypsum Board 01 | 70 | Sqm | 25% | 35 | 2450
|  |  |  | Taping Jointing 01 | 70 | Sqm | 15% | 21 | 1470
|  |  |  | Taping Jointing 02 | 70 | Sqm | 15% | 21 | 1470
|  |  |  | Sanding | 70 | Sqm | 5% | 7 | 490
4.02 | Ceiling |  | GYPSUM CEILING - 60 x 60 Supply and installation of 60 x 60 ceiling tile |  | 249 | Sqm |  | 110 | 27390
|  |  |  | Frame 01 | 249 | Sqm | 40% | 44 | 10956
|  |  |  | Tile Fixing | 249 | Sqm | 25% | 27.5 | 6847.5
4.03 | Ceiling |  | GYPSUM CEILING COVE Supply and installation of gypsum cove for the LED and cut outs for the lights and AC grills including paint finish ( Jotun Fenomastic or Equivalent) Location : Vet Reception Area |  | 1 | Item |  | 5000 | 5000
|  |  |  | Frame 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Gypsum Board 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Taping Jointing 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Taping Jointing 02 | 1 | Nos | 5% | 250 | 250
|  |  |  | Sanding | 1 | Nos | 5% | 250 | 250
|  |  |  | Paint | 1 | Nos | 25% | 1250 | 1250
|  |  |  | Cut Outs | 1 | Nos | 35% | 1750 | 1750
4.04 | Joinery |  | WOODEN CEILING AT THE VET AREA supply and installation of wooden ceiling at the VET area - MDF with veneer finish Area considered : 20 Sqm Chandelier is excluded |  | 1 | Item |  | 13387 | 13387
|  |  |  | Frame 01 | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Veneer | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Polish | 1 | Nos | 15% | 2008.05 | 2008.05
|  |  |  | Assembly | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Site Fixing | 1 | Nos | 25% | 3346.75 | 3346.75
5 |  |  | GLASS AND ALUMINUM
5.01 | Glass |  | Supply and installation of fixed glass partition. max.ht up to 3m |  | 24 | Sqm |  | 450 | 10800
|  |  |  | Channels | 24 | Nos | 20% | 90 | 2160
|  |  |  | Glass Fixing | 24 | Nos | 60% | 270 | 6480
|  |  |  | Finishing Joints | 24 | Nos | 15% | 67.5 | 1620
|  |  |  | Cleaning | 24 | Nos | 5% | 22.5 | 540
6 |  |  | JOINERY
| Joinery |  | Manufacture, supply and installation of Reception Counter with build in storage made of MDF with all related works as per design. Exclude Signage |  | 1 | Nos |  | 20350 | 20350
|  |  |  | Frame 01 | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Veneer | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Polish | 1 | Nos | 10% | 2035 | 2035
|  |  |  | Assembly | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Site Fixing | 1 | Nos | 30% | 6105 | 6105
7 | Joinery |  | Manufacture, supply and installation of L Shape Planter Box made of MDF with all related works as per design. Exclude Plants |  | 1 | Nos |  | 4530 | 4530
|  |  |  | Frame 01 | 1 | Nos | 30% | 1359 | 1359
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1359 | 1359
|  |  |  | Site Fixing | 1 | Nos | 40% | 1812 | 1812
8 | Joinery |  | Manufacture, supply and installation of Banquette Seating with Projections made of MDF with all related works as per design. Exclude: Plants ¦ @ Cat Waiting Area Note-Aed 60-70 Leather consider |  | 1 | Nos |  | 5850 | 5850
|  |  |  | Frame 01 | 1 | Nos | 30% | 1755 | 1755
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1755 | 1755
|  |  |  | Site Fixing | 1 | Nos | 40% | 2340 | 2340
9 | Joinery |  | Manufacture, supply and installation of Two Tier Banquette Seating with Steps at center made of MDF with all related works as per design. @ Dog Waiting Area Note-Aed 60-70 Leather consider |  | 1 | Nos |  | 5000 | 5000
|  |  |  | Frame 01 | 1 | Nos | 30% | 1500 | 1500
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1500 | 1500
|  |  |  | Site Fixing | 1 | Nos | 40% | 2000 | 2000
10 | Joinery |  | Manufacture, supply and installation of Banquette Seating made of MDF with all related works as per design. @ Dog Waiting Area |  | 1 | Nos |  | 3350 | 3350
|  |  |  | Frame 01 | 1 | Nos | 30% | 1005 | 1005
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1005 | 1005
|  |  |  | Site Fixing | 1 | Nos | 40% | 1340 | 1340
11 | Joinery |  | Manufacture, supply and installation of Planter Box made of MDF with all related works as per design. Exclude: Plants @ Behing Banquette Sitting at Cat Waiting Area |  | 1 | Nos |  | 6905 | 6905
|  |  |  | Frame 01 | 1 | Nos | 30% | 2071.5 | 2071.5
|  |  |  | Laminate Finish | 1 | Nos | 30% | 2071.5 | 2071.5
|  |  |  | Site Fixing | 1 | Nos | 40% | 2762 | 2762
12 | Joinery |  | Manufacture, supply and installation of DB Wall Cladding Cabinet Type made of MDF all related works as per design. |  | 1 | Nos |  | 7150 | 7150
|  |  |  | Frame 01 | 1 | Nos | 30% | 2145 | 2145
|  |  |  | Laminate Finish | 1 | Nos | 30% | 2145 | 2145
|  |  |  | Site Fixing | 1 | Nos | 40% | 2860 | 2860
13 | Joinery |  | Manufacture, supply and installation of Display Cabinet with Under Storage made of MDF with all related works as per design. @ Near Reception Desk Note-LED Light Excluded |  | 2 | Nos |  | 5000 | 10000
|  |  |  | Frame 01 | 2 | Nos | 30% | 1500 | 3000
|  |  |  | Laminate Finish | 2 | Nos | 30% | 1500 | 3000
|  |  |  | Site Fixing | 2 | Nos | 40% | 2000 | 4000
14 | Joinery |  | Manufacture, supply and installation of Cabinet with Sink made of MDF with all related works as per design. Exclude all Appliences and MEP works |  | 1 | Nos |  | 19880 | 19880
|  |  |  | Frame 01 | 1 | Nos | 30% | 5964 | 5964
|  |  |  | Laminate Finish | 1 | Nos | 20% | 3976 | 3976
|  |  |  | Site Fixing | 1 | Nos | 50% | 9940 | 9940
15 | Joinery |  | Manufacture, supply and installation of Cabinet with Sink made of MDF with all related works as per design. Exclude all Appliences and MEP works |  | 1 | Nos |  | 22500 | 22500
|  |  |  | Frame 01 | 1 | Nos | 30% | 6750 | 6750
|  |  |  | Laminate Finish | 1 | Nos | 20% | 4500 | 4500
|  |  |  | Site Fixing | 1 | Nos | 50% | 11250 | 11250
16 | Joinery |  | Manufacture, supply and installationn of Preparation Cabinet made of MDF with all related works as per design. |  | 1 | Nos |  | 5600 | 5600
|  |  |  | Frame 01 | 1 | Nos | 30% | 1680 | 1680
|  |  |  | Laminate Finish | 1 | Nos | 20% | 1120 | 1120
|  |  |  | Site Fixing | 1 | Nos | 50% | 2800 | 2800
17 | Joinery |  | Manufacture, supply and installationn of Preparation Table made of MDF with all related works as per design. |  | 2 | Nos |  | 6500 | 13000
|  |  |  | Frame 01 | 2 | Nos | 30% | 1950 | 3900
|  |  |  | Laminate Finish | 2 | Nos | 20% | 1300 | 2600
|  |  |  | Site Fixing | 2 | Nos | 50% | 3250 | 6500
18 | Joinery |  | Manufacture, supply and installation of Wooden Battern Ceiling made of MDF with all related works as per design. Note-200 mm hight consider |  | 1 | Nos |  | 15000 | 15000
|  |  |  | Frame 01 | 1 | Nos | 30% | 4500 | 4500
|  |  |  | Laminate Finish | 1 | Nos | 20% | 3000 | 3000
|  |  |  | Site Fixing | 1 | Nos | 50% | 7500 | 7500
19 | Joinery |  | Timber doors and frames; including ironmongery, architrave, fittings, fixings and accessories; all in accordance with the drawings and Specifications. Single leaf concealed door closer |  | 8 | Nos |  | 3100 | 24800
|  |  |  | Frame 01 | 8 | Nos | 30% | 930 | 7440
|  |  |  | Laminate Finish | 8 | Nos | 20% | 620 | 4960
|  |  |  | Site Fixing | 8 | Nos | 50% | 1550 | 12400
20 | Joinery |  | Timber doors and frames; including ironmongery, architrave, fittings, fixings and accessories; all in accordance with the drawings and Specifications. Single leaf , with vision panel concealed door closer |  | 1 | Nos |  | 3500 | 3500
|  |  |  | Frame 01 | 1 | Nos | 30% | 1050 | 1050
|  |  |  | Laminate Finish | 1 | Nos | 20% | 700 | 700
|  |  |  | Site Fixing | 1 | Nos | 50% | 1750 | 1750
[9 empty] | 420250 |  |  |  | 23490 | 6652.8 | 20833.2
1.583%
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amount / Rate

## Work Progress Report
Sl No | Category | Dwg Code | Description (Task) | Sub Task | QTY | UNIT | Breakdown % | RATE | AMOUNT | Previous % | Current % | Total % | Previous Qty | Current Qty | Total Qty | Cum Amt | Current Amt | Total Amt
1 |  |  | PARTITION AND LINING
1.01 | Partition / Lining |  | 100mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 4.0m. Location :Veterinary Clinic |  | 472 | Sqm |  | 108 | 50976 | 46.08% | 13.05% | 59.13% | 217.5 | 61.6 | 279.1 | 23490 | 6652.8 | 20833.2
|  |  |  | Frame 01 | 472 | Sqm | 30% | 32.4 | 15292.8 |  |  |  | 400 | 72 | 0 | 12960 | 2332.8 | 0
|  |  |  | Gypsum Board 01 | 472 | Sqm | 15% | 16.2 | 7646.4 |  |  |  | 300 | 100 | 72 | 4860 | 1620 | 1166.4
|  |  |  | Rockwool | 472 | Sqm | 10% | 10.8 | 5097.6 |  |  |  | 300 | 100 | 72 | 3240 | 1080 | 777.6
|  |  |  | Gypsum Board 02 | 472 | Sqm | 15% | 16.2 | 7646.4 |  |  |  | 150 | 100 | 222 | 2430 | 1620 | 3596.4
|  |  |  | Taping Jointing 01 | 472 | Sqm | 15% | 16.2 | 7646.4 |  |  |  | 0 |  | 472 | 0 | 0 | 7646.4
|  |  |  | Taping Jointing 02 | 472 | Sqm | 10% | 10.8 | 5097.6 |  |  |  | 0 |  | 472 | 0 | 0 | 5097.6
|  |  |  | Sanding | 472 | Sqm | 5% | 5.4 | 2548.8 |  |  |  | 0 |  | 472 | 0 | 0 | 2548.8
1.02 | Partition / Lining |  | 200 mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 4.0m. Location :Veterinary Clinic |  | 72 | Sqm |  | 210 | 15120
|  |  |  | Frame 01 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Frame 02 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Gypsum Board 01 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Rockwool | 72 | Sqm | 10% | 21 | 1512
|  |  |  | Gypsum Board 02 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Taping Jointing 01 | 72 | Sqm | 15% | 31.5 | 2268
|  |  |  | Taping Jointing 02 | 72 | Sqm | 10% | 21 | 1512
|  |  |  | Sanding | 72 | Sqm | 5% | 10.5 | 756
1.03 | Partition / Lining |  | 100mm thick Supply and installation of Gypsum board 12.5mm thick single gypsum board with rockwool 18kg/m3 installation inside; height up to 1.2m. Location :Veterinary Clinic |  | 13.2 | Sqm |  | 110 | 1452
|  |  |  | Frame 01 | 13.2 | Sqm | 30% | 33 | 435.6
|  |  |  | Gypsum Board 01 | 13.2 | Sqm | 15% | 16.5 | 217.8
|  |  |  | Rockwool | 13.2 | Sqm | 10% | 11 | 145.2
|  |  |  | Gypsum Board 02 | 13.2 | Sqm | 15% | 16.5 | 217.8
|  |  |  | Taping Jointing 01 | 13.2 | Sqm | 15% | 16.5 | 217.8
|  |  |  | Taping Jointing 02 | 13.2 | Sqm | 10% | 11 | 145.2
|  |  |  | Sanding | 13.2 | Sqm | 5% | 5.5 | 72.6
1.04 | Partition / Lining |  | Supply and installation of gypsum lining on the existing block wall 12.5mm thick Gypsum board with 75mm stud of height max upto 4.0m. Location :Veterinary Clinic |  | 188 | Sqm |  | 95 | 17860
|  |  |  | Frame 01 | 188 | Sqm | 30% | 28.5 | 5358
|  |  |  | Gypsum Board 01 | 188 | Sqm | 15% | 14.25 | 2679
|  |  |  | Taping Jointing 01 | 188 | Sqm | 15% | 14.25 | 2679
|  |  |  | Taping Jointing 02 | 188 | Sqm | 10% | 9.5 | 1786
|  |  |  | Sanding | 188 | Sqm | 5% | 4.75 | 893
2 |  |  | FLOORING WORKS
2.01 | Floor |  | F-102 VINYL FLOORING Supply of flooring - Straight Pattern as per the sample submitted and approved by the client, to be installed by Glue on smooth, levelled, clear and dry floor. Considered oak wood effect sheet vinyl as per client instruction Suitable for clinics. |  | 166 | Sqm |  | 140 | 23240
2.02 | Floor |  | F-102 VINYL FLOORING Installation of the flooring including self leveling |  | 166 | Sqm |  | 80 | 13280
|  |  |  | Self Levelling | 166 | Sqm | 60% | 48 | 7968
|  |  |  | Installation of Vinyl | 166 | Sqm | 40% | 32 | 5312
2.03 | Floor |  | F-300 MOSAIC TILE FLOORING Supply and installation of tile flooring 60x120x9mm Porcelain Matt P.C Rate of AED 110.00 per sqm |  | 52 | Sqm |  | 165 | 8580
|  |  |  | Tile Fixing | 52 | Sqm | 90% | 148.5 | 7722
|  |  |  | Grout | 52 | Sqm | 10% | 16.5 | 858
2.04 | Floor |  | F-305 TILE FLOORING Supply and installation of tile flooring 20x120x9mm Porcelain Matt. P.C Rate of AED 90.00 per sqm Reception |  | 18 | Sqm |  | 145 | 2610
|  |  |  | Tile Fixing | 18 | Sqm | 90% | 130.5 | 2349
|  |  |  | Grout | 18 | Sqm | 10% | 14.5 | 261
2.05 | Floor |  | SKIRTING Supply and installation of wooden skirting |  | 299 | Lm |  | 60 | 17940
|  |  |  | Skirting Fixing | 299 | Sqm | 90% | 54 | 16146
|  |  |  | Grout | 299 | Sqm | 10% | 6 | 1794
2.06 | Floor |  | Trim Supply and installation of transition strips on areas with different finishes |  | 12 | Lm |  | 90 | 1080
3 |  |  | WALL FINISHES
3.01 | Paint |  | PAINT FINISH-W200 Supply and apply of paint finish Location : GF/MF Considered alternative option Jotun Fenomastic paint finish |  | 105 | Sqm |  | 30 | 3150
|  |  |  | Primer | 105 | Sqm | 15% | 4.5 | 472.5
|  |  |  | Stucco 01 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Stucco 02 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Paint 01 | 105 | Sqm | 20% | 6 | 630
|  |  |  | Paint 02 | 105 | Sqm | 25% | 7.5 | 787.5
3.02 | Paint |  | PAINT FINISH-W202 Supply and apply of new paint finish Location : GF/MF Jotun Fenomastic or equivalent |  | 39 | Sqm |  | 30 | 1170
|  |  |  | Primer | 39 | Sqm | 15% | 4.5 | 175.5
|  |  |  | Stucco 01 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Stucco 02 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Paint 01 | 39 | Sqm | 20% | 6 | 234
|  |  |  | Paint 02 | 39 | Sqm | 25% | 7.5 | 292.5
3.03 | Paint |  | ANTIMICROBIAL PAINT FINISH -W204 Supply and installation of new paint finish Location : GF/MF Jotun or equivalent |  | 750 | Sqm |  | 40 | 30000
|  |  |  | Primer | 750 | Sqm | 15% | 6 | 4500
|  |  |  | Stucco 01 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Stucco 02 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Paint 01 | 750 | Sqm | 20% | 8 | 6000
|  |  |  | Paint 02 | 750 | Sqm | 25% | 10 | 7500
4 |  |  | CEILING WORKS
4.01 | Ceiling |  | GYPSUM CEILING Supply and installation of 12.5mm thick one layer of MR gypsum board ceiling including paint finish ( Jotun Fenomastic or Equivalent) Location : Vet Reception Area |  | 70 | Sqm |  | 140 | 9800
|  |  |  | Frame 01 | 70 | Sqm | 40% | 56 | 3920
|  |  |  | Gypsum Board 01 | 70 | Sqm | 25% | 35 | 2450
|  |  |  | Taping Jointing 01 | 70 | Sqm | 15% | 21 | 1470
|  |  |  | Taping Jointing 02 | 70 | Sqm | 15% | 21 | 1470
|  |  |  | Sanding | 70 | Sqm | 5% | 7 | 490
4.02 | Ceiling |  | GYPSUM CEILING - 60 x 60 Supply and installation of 60 x 60 ceiling tile |  | 249 | Sqm |  | 110 | 27390
|  |  |  | Frame 01 | 249 | Sqm | 40% | 44 | 10956
|  |  |  | Tile Fixing | 249 | Sqm | 25% | 27.5 | 6847.5
4.03 | Ceiling |  | GYPSUM CEILING COVE Supply and installation of gypsum cove for the LED and cut outs for the lights and AC grills including paint finish ( Jotun Fenomastic or Equivalent) Location : Vet Reception Area |  | 1 | Item |  | 5000 | 5000
|  |  |  | Frame 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Gypsum Board 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Taping Jointing 01 | 1 | Nos | 10% | 500 | 500
|  |  |  | Taping Jointing 02 | 1 | Nos | 5% | 250 | 250
|  |  |  | Sanding | 1 | Nos | 5% | 250 | 250
|  |  |  | Paint | 1 | Nos | 25% | 1250 | 1250
|  |  |  | Cut Outs | 1 | Nos | 35% | 1750 | 1750
4.04 | Joinery |  | WOODEN CEILING AT THE VET AREA supply and installation of wooden ceiling at the VET area - MDF with veneer finish Area considered : 20 Sqm Chandelier is excluded |  | 1 | Item |  | 13387 | 13387
|  |  |  | Frame 01 | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Veneer | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Polish | 1 | Nos | 15% | 2008.05 | 2008.05
|  |  |  | Assembly | 1 | Nos | 20% | 2677.4 | 2677.4
|  |  |  | Site Fixing | 1 | Nos | 25% | 3346.75 | 3346.75
5 |  |  | GLASS AND ALUMINUM
5.01 | Glass |  | Supply and installation of fixed glass partition. max.ht up to 3m |  | 24 | Sqm |  | 450 | 10800
|  |  |  | Channels | 24 | Nos | 20% | 90 | 2160
|  |  |  | Glass Fixing | 24 | Nos | 60% | 270 | 6480
|  |  |  | Finishing Joints | 24 | Nos | 15% | 67.5 | 1620
|  |  |  | Cleaning | 24 | Nos | 5% | 22.5 | 540
6 |  |  | JOINERY
| Joinery |  | Manufacture, supply and installation of Reception Counter with build in storage made of MDF with all related works as per design. Exclude Signage |  | 1 | Nos |  | 20350 | 20350
|  |  |  | Frame 01 | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Veneer | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Polish | 1 | Nos | 10% | 2035 | 2035
|  |  |  | Assembly | 1 | Nos | 20% | 4070 | 4070
|  |  |  | Site Fixing | 1 | Nos | 30% | 6105 | 6105
7 | Joinery |  | Manufacture, supply and installation of L Shape Planter Box made of MDF with all related works as per design. Exclude Plants |  | 1 | Nos |  | 4530 | 4530
|  |  |  | Frame 01 | 1 | Nos | 30% | 1359 | 1359
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1359 | 1359
|  |  |  | Site Fixing | 1 | Nos | 40% | 1812 | 1812
8 | Joinery |  | Manufacture, supply and installation of Banquette Seating with Projections made of MDF with all related works as per design. Exclude: Plants ¦ @ Cat Waiting Area Note-Aed 60-70 Leather consider |  | 1 | Nos |  | 5850 | 5850
|  |  |  | Frame 01 | 1 | Nos | 30% | 1755 | 1755
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1755 | 1755
|  |  |  | Site Fixing | 1 | Nos | 40% | 2340 | 2340
9 | Joinery |  | Manufacture, supply and installation of Two Tier Banquette Seating with Steps at center made of MDF with all related works as per design. @ Dog Waiting Area Note-Aed 60-70 Leather consider |  | 1 | Nos |  | 5000 | 5000
|  |  |  | Frame 01 | 1 | Nos | 30% | 1500 | 1500
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1500 | 1500
|  |  |  | Site Fixing | 1 | Nos | 40% | 2000 | 2000
10 | Joinery |  | Manufacture, supply and installation of Banquette Seating made of MDF with all related works as per design. @ Dog Waiting Area |  | 1 | Nos |  | 3350 | 3350
|  |  |  | Frame 01 | 1 | Nos | 30% | 1005 | 1005
|  |  |  | Laminate Finish | 1 | Nos | 30% | 1005 | 1005
|  |  |  | Site Fixing | 1 | Nos | 40% | 1340 | 1340
11 | Joinery |  | Manufacture, supply and installation of Planter Box made of MDF with all related works as per design. Exclude: Plants @ Behing Banquette Sitting at Cat Waiting Area |  | 1 | Nos |  | 6905 | 6905
|  |  |  | Frame 01 | 1 | Nos | 30% | 2071.5 | 2071.5
|  |  |  | Laminate Finish | 1 | Nos | 30% | 2071.5 | 2071.5
|  |  |  | Site Fixing | 1 | Nos | 40% | 2762 | 2762
12 | Joinery |  | Manufacture, supply and installation of DB Wall Cladding Cabinet Type made of MDF all related works as per design. |  | 1 | Nos |  | 7150 | 7150
|  |  |  | Frame 01 | 1 | Nos | 30% | 2145 | 2145
|  |  |  | Laminate Finish | 1 | Nos | 30% | 2145 | 2145
|  |  |  | Site Fixing | 1 | Nos | 40% | 2860 | 2860
13 | Joinery |  | Manufacture, supply and installation of Display Cabinet with Under Storage made of MDF with all related works as per design. @ Near Reception Desk Note-LED Light Excluded |  | 2 | Nos |  | 5000 | 10000
|  |  |  | Frame 01 | 2 | Nos | 30% | 1500 | 3000
|  |  |  | Laminate Finish | 2 | Nos | 30% | 1500 | 3000
|  |  |  | Site Fixing | 2 | Nos | 40% | 2000 | 4000
14 | Joinery |  | Manufacture, supply and installation of Cabinet with Sink made of MDF with all related works as per design. Exclude all Appliences and MEP works |  | 1 | Nos |  | 19880 | 19880
|  |  |  | Frame 01 | 1 | Nos | 30% | 5964 | 5964
|  |  |  | Laminate Finish | 1 | Nos | 20% | 3976 | 3976
|  |  |  | Site Fixing | 1 | Nos | 50% | 9940 | 9940
15 | Joinery |  | Manufacture, supply and installation of Cabinet with Sink made of MDF with all related works as per design. Exclude all Appliences and MEP works |  | 1 | Nos |  | 22500 | 22500
|  |  |  | Frame 01 | 1 | Nos | 30% | 6750 | 6750
|  |  |  | Laminate Finish | 1 | Nos | 20% | 4500 | 4500
|  |  |  | Site Fixing | 1 | Nos | 50% | 11250 | 11250
16 | Joinery |  | Manufacture, supply and installationn of Preparation Cabinet made of MDF with all related works as per design. |  | 1 | Nos |  | 5600 | 5600
|  |  |  | Frame 01 | 1 | Nos | 30% | 1680 | 1680
|  |  |  | Laminate Finish | 1 | Nos | 20% | 1120 | 1120
|  |  |  | Site Fixing | 1 | Nos | 50% | 2800 | 2800
17 | Joinery |  | Manufacture, supply and installationn of Preparation Table made of MDF with all related works as per design. |  | 2 | Nos |  | 6500 | 13000
|  |  |  | Frame 01 | 2 | Nos | 30% | 1950 | 3900
|  |  |  | Laminate Finish | 2 | Nos | 20% | 1300 | 2600
|  |  |  | Site Fixing | 2 | Nos | 50% | 3250 | 6500
18 | Joinery |  | Manufacture, supply and installation of Wooden Battern Ceiling made of MDF with all related works as per design. Note-200 mm hight consider |  | 1 | Nos |  | 15000 | 15000
|  |  |  | Frame 01 | 1 | Nos | 30% | 4500 | 4500
|  |  |  | Laminate Finish | 1 | Nos | 20% | 3000 | 3000
|  |  |  | Site Fixing | 1 | Nos | 50% | 7500 | 7500
19 | Joinery |  | Timber doors and frames; including ironmongery, architrave, fittings, fixings and accessories; all in accordance with the drawings and Specifications. Single leaf concealed door closer |  | 8 | Nos |  | 3100 | 24800
|  |  |  | Frame 01 | 8 | Nos | 30% | 930 | 7440
|  |  |  | Laminate Finish | 8 | Nos | 20% | 620 | 4960
|  |  |  | Site Fixing | 8 | Nos | 50% | 1550 | 12400
20 | Joinery |  | Timber doors and frames; including ironmongery, architrave, fittings, fixings and accessories; all in accordance with the drawings and Specifications. Single leaf , with vision panel concealed door closer |  | 1 | Nos |  | 3500 | 3500
|  |  |  | Frame 01 | 1 | Nos | 30% | 1050 | 1050
|  |  |  | Laminate Finish | 1 | Nos | 20% | 700 | 700
|  |  |  | Site Fixing | 1 | Nos | 50% | 1750 | 1750
[9 empty] | 420250 | [6 empty] | 23490 | 6652.8 | 20833.2
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amount / Rate
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amount / Rate